## Sheet4
ID | Risk | Description (Impact) | Mitigation strategy
CEAV Safety Risks
| AVs operating with non AV and CV vehicles | - When something new or unknown is on the road, there is possibility of distraction or confusion | - AV can sufficiently react to the other vehicles if they do something unexpected
| AVs operating at low speed with vehicles at higher speeds | - Risk of tailgating (uncomfortable for passengers) - Risk of being rear-ended | - May Mobility increased operational speed to 20 mph with latest software release - Fleet Attendant expected to use best judgment to help mitigate
| Ensuring pedestrian safety for interactions with AVs | - A common misconception is that a pedestrian may step out and not be detected by the AV | - The suite of sensors and cameras on the car ensure AV knowledge of pedestrians from a safe distance - Redundant systems in place, just in case: Fleet Attendant and RSUs
| Ensuring bike and scooter safety for interaction with AVs | - Scooter is a new mode that may interact with an AV | - AV can detect scooters and bikes similarly to all other moving objects, with its suite of sensors and redundant systems, so that it can appropriately react - This was specifically tested in preliminary testing
| Interaction with the pedestrian and cyclists - comfort with the presence of AV on the roadway | False security of safety around AV | - AV can detect scooters and bikes similarly to all other moving objects, with its suite of sensors and redundant systems, so that it can appropriately react - Fleet Attendants are trained to be wary of and careful with bicyclists. They are to step in if the vehicle interaction with a bicyclist or pedestrian is causing discomfort inside or outside of the car (i.e. if AV is following slowly behind a bike in autonomy, FA to take over and change lanes to safely pass it)
| Analyzing latency and high network traffic problems in connectivity through communications with other road users and infrastructure and to the data management hub | For RFP 2 | - This may be accounted for in data insights, if applicable
| Handling uncertainty due to unpredictable operation of non-automated vehicles, other road users, and environmental conditions |  | - Sensor suite accounts for this - Further sensor development - Fleet Attendant training
| No certification, testing, and rating systems for safe pre-deployment evaluation methods for these shuttles currently exist. | The most important technical problem blocking the deployment of CEAVs in a smart city to enhance mobility is that no certification, testing, and rating systems for safe pre-deployment evaluation methods for these shuttles currently exist. | - Factory, Preliminary, and Final testing - Tabletop meeting - Various permits and registration
| CEAV operator not trained to handle emergency situations/ real time situations |  | - Emergency situations are covered in Fleet Attendent training. Please refer to SOP for details.
| CEAV operator is distracted and unable to handle emergency/real-time situations |  | - Distracted driving is covered in training, and there is disciplinary action taken in instances where it occurs
| A failure condition occurs if the CEAV is not able to make it to a charging station before losing charge | AV may stop on the roadway before it is able to charge and cause a crash | - On-site technician radioed to scene - Alternate vehicle to replace previous vehicle if it was still on the route - Vehicles are charged nightly
| Road conditions (lane closures, conditions) and not updated the CEAV maps | AV will not understand current roadway conditions | - Fleet Attendant will take over
| When the communication fails between the CVs and AVs | AV would not receive CV messages | - Fleet Attendant will take over
| Can passengers tamper with the controls of the CEAV since it is driverless | Vehicle may be stopped on the roadway | - Fleet Attendant on board at all times
| Time when AVs might not be in operation and passengers not knowing about it and wait for the FMLM service | No new hazard (impact is the same as current COTA stops) | - Public-facing site will be updated by Jennifer - May Mobility platforms will be updated - Possible signage at each stop
| Crash along the route is not detected by the AV | AV would not receive CV messages | - Fleet Attendant will take over if needed - Alternate route if needed
| AV encounters situation outside its design domain (obstruction, road conditions, snow, etc.) | - Unknown response from vehicle | - Fleet Attendant will take over
| Law enforcement officials not trained to handle emergency situations with the AVs | - Possibility of safety risk to the responders - Possibility of an ineffective response, therefore risk to any involved in emergency | - Alignment call with Commander Springer - Tabletop activity - three representatives from PD were present - Comm. Springer to send out an email and an intranet post to inform PD of AVs, include safety video, and answer FAQs
| Emergency response not trained to handle EVs | Safety risk to the responders | - Tabletop meeting - Commander Springer to send out email - Safety video - May Mobility contact information
| Passengers not knowing the stops for the alternate routes of the AVs. | Only consider if physical harm is possible or outside the risks of current COTA operations | - Jennifer to update public-facing site - Possible FAQ section
| https://www.transportation.gov/sites/dot.gov/files/docs/policy-initiatives/automated-vehicles/320711/preparing-future-transportation-automated-vehicle-30.pdf | Check this for any new risks (may be n/a)
| Other options when the AVs are not available and the riders not updated about the availability | Consider whether there is an impact here
| Pre-time dwell may not accommodate an entire loading (for multi-passenger parties, ADA customers, etc.) | Parties are separated (people - young children, for example, are left behind) | - Fleet Attendant will take over
| ADA equipment could become dislodged during AV operations (some current operators are not ADA accessible or compliant; others are only accessible) |  | - See ADA interim plan
| what happens when some of the operation scenarios and sensors fail and the passengers aren't trained to handle the AV |  | - Fleet Attendant on board at all times
| what happens if there is flat tire or some kind of AV maintenance that a non AV experience |  | - May has an on-site technician that will be radioed to the scene
| how will they react with the construction zone and the lane marking are not marked and have construction cones to guide the traffic |  | - Sensors will take them into account - Fleet Attendant to take over when necessary